## Sheet2
|  | Expected Date | Status
ENQUIRY FORM
1 | IF I ENTER NAME OR MOBILE OR EMAIL THEN IT SHOULD SEARCH THE CUSTOMER | 2014-07-03 | Done
AGREEMENT TEMPLATE
2 | MAKE A NEW TEMPLATE FOR AGREEMENT TEMPLATE | 20/3/2014 | In Progress
3 | TAX TEMPLATE MASTER - THERE SHOULD BE AN OPTION TO ADD A SERVICE TAX ON VALUE OF THE FLAT | 2014-07-03 | In Progress
PROJECT CONFIGURATOR:
4 | WHEN THE AREA OF THE FLAT IS 0, IN CASE OF REFUGE AREA, THEN THAT FLAT(S) SHOULD NOT BE CONSIDERED IN THE INVENTORY COUNT. SO IF THERE ARE 88 FLATS IN A BUILDING AND 2 ARE REFUGE FLATS, THEN NO OF UNITS SHOULD BE 86 AND NOT 88. | 2014-11-03 | In Progress
5 | THERE SHOULD BE A PROJECTWISE TEMPLATE TO CALCULATE AGREEMENT VALUE. |  | Option on Booking Master
EXAMPLE:
AREA X RATE + INFRASTRUCTURE CHARGES + VAT
OR
AREA X RATE + INFRASTRUCTURE CHARGES
OR
AREA X RATE + INFRASTRUCTURE CHARGES + INCIDENTAL CHARGES + VAT
SO CREATE A TEMPLATE WHERE I CAN DEFINE THESE
6 | DEFINITION OF UNITS. IN ADDITION TO THE EXISTING POSSIBILITIES, THE SOFTWARE SHOULD BE ABLE TO ADD ODD AND EVEN FLOORS, | 2014-12-03 | In Progress
| OR ON EVERY FLOOR I SHOULD BE ABLE TO INDIVIDUALLY DEFINE NO OF UNITS AND THEIR AREAS. IN CASE IF THERE ARE COMMERCIAL SHOPS ON THE GROUND FLOOR AND FLATS FROM 1ST FLOOR ONWARDS, IT SHOULD HANDLE. | 14/3/2014 | In Progress
7 | MAKE A TEMPLATE FOR PAYMENT SCHEDULE TEMPLATE: | 17/3/2014
FORMAT:
STAGE, PERCENTAGE
8 | I SHOULD BE ABLE TO SELECT A TEMPLATE FOR A PROJECT IN THE PROJECT CONFIGURATOR AND ALSO BE ABLE TO MODIFY THE PERCENTAGES. |  | Selection of payment schedule will be on Booking Master
BOOKING FORM:
9 | IN THE BOOKING FORM, KEEP A FACILITY TO SEARCH THE CUSTOMER BY EITHER SELECTING CUSTOMER NAME OR BY ENTERING MOBILE NO OR EMAIL ID. THE SYSTEM SHOULD DETECT DUPLICATION BY MATCHING NAME WITH MOBILE NO OR EMAIL ID. | 2014-10-03 | In Progress
10 | I SHOULD BE ABLE TO EDIT THE RATE EVEN AFTER I HAVE SAVED THE BOOKING. | 2014-10-03 | In Progress
11 | AT THE TIME OF BOOKING WHEN I CREATE A RECEIPT, THE NARRATION SHOULD BE TOWARDS INTEREST FREE DEPOSIT. ONCE THE FLAT IS REGISTERED THEN THE NARRATION OF THE INITIAL RECEIPT SHOULD AUTOMATICALLY BE UPDATED TO TOWARDS FLAT NO.
12 | IN THE BOOKING FORM THERE ARE 3 APPLICANTS | 2014-11-03 | In Progress
SO THERE SHOULD BE D.O.B. OF ALL 3 APPLICANTS AND PAN COPY OF ALL 3 APPLICANTS NO SPOUSE
13 | IN THE BOOKING FORM REMOVE TDS, REMOVE PARKING REQUIRED, NOT REQUIRED | 2014-11-03 | In Progress
14 | BROKERAGE PERCENTAGE 2% BY DEFAULT CACULATION TO BE ON AREA X RATE. IT SHOULD AUTO CALCULATE | 2014-12-03 | In Progress
15 | THERE SHOULD BE A FACILITY TO SELECT PAYMENT SCHEDULE FOR INDIVIDUAL CUSTOMER FROM THE TEMPLATE. IN ADDITION, I SHOULD BE ABLE TO MODIFY THE PERCENTAGES IF I WANT TO. |  | To be add After payment schedule template
16 | ADD RTGS OPTION NEXT TO CASH/CHEQUE/DEMAND DRAFT | 2014-12-03 | In Progress
FOLLOW UP DETAILS:
17 | PUT A DATE RANGE INSTEAD OF AS ON DATE | 14/3/2014 | In Progress
ISSUE SUBJECT MASTER:
LOGIC:
18 | KARIA WANTS TO DEFINE AN ANSWER TO EVERY ISSUE. SO BELOW THE SUBJECT, ADD A TEXT BOX FOR THEM TO DEFINE THE ANSWER TO THAT QUESTION. | 20/3/2014 | In Progress
CUSTOMER GRIEVANCE:
19 | THE ORDER OF THE GRID TO BE CHANGED | 14/3/2014 | Done
PROJECT, CUSTOMER, FLAT NO……….RELATED TO, ISSUE
20 | WHEN I CLICK ON SAVE, THE SOFTWARE SHOULD AUTOMATICALLY SEND AN EMAIL AND SMS TO THE CUSTOMER | 19/3/2014
RECEIPT VOUCHER:
21 | IN THE RECEIPT VOUCHER THERE SHOULD BE A GRID | 20/3/2014 | In Progress
AMOUNT, TO BE ADJUSTED AGAINST.
PAYMENT FOLLOW UP:
22 | THE DATA OF ALL EMPLOYEES SHOULD BE VISIBLE TO ALL USERS. | 21/3/2014 | Done

## Sheet3
ENQUIRY FORM
1 | IF I ENTER NAME OR MOBILE OR EMAIL THEN IT SHOULD SEARCH THE CUSTOMER
AGREEMENT TEMPLATE
2 | MAKE A NEW TEMPLATE FOR AGREEMENT TEMPLATE
3 | TAX TEMPLATE MASTER - THERE SHOULD BE AN OPTION TO ADD A SERVICE TAX ON VALUE OF THE FLAT
PROJECT CONFIGURATOR:
4 | WHEN THE AREA OF THE FLAT IS 0, IN CASE OF REFUGE AREA, THEN THAT FLAT(S) SHOULD NOT BE CONSIDERED IN THE INVENTORY COUNT. SO IF THERE ARE 88 FLATS IN A BUILDING AND 2 ARE REFUGE FLATS, THEN NO OF UNITS SHOULD BE 86 AND NOT 88.
5 | THERE SHOULD BE A PROJECTWISE TEMPLATE TO CALCULATE AGREEMENT VALUE.
EXAMPLE:
AREA X RATE + INFRASTRUCTURE CHARGES + VAT
OR
AREA X RATE + INFRASTRUCTURE CHARGES
OR
AREA X RATE + INFRASTRUCTURE CHARGES + INCIDENTAL CHARGES + VAT
SO CREATE A TEMPLATE WHERE I CAN DEFINE THESE
6 | DEFINITION OF UNITS. IN ADDITION TO THE EXISTING POSSIBILITIES, THE SOFTWARE SHOULD BE ABLE TO ADD ODD AND EVEN FLOORS,
OR ON EVERY FLOOR I SHOULD BE ABLE TO INDIVIDUALLY DEFINE NO OF UNITS AND THEIR AREAS. IN CASE IF THERE ARE COMMERCIAL SHOPS ON THE GROUND FLOOR AND FLATS FROM 1ST FLOOR ONWARDS, IT SHOULD HANDLE.
7 | MAKE A TEMPLATE FOR PAYMENT SCHEDULE TEMPLATE:
FORMAT:
STAGE, PERCENTAGE
8 | I SHOULD BE ABLE TO SELECT A TEMPLATE FOR A PROJECT IN THE PROJECT CONFIGURATOR AND ALSO BE ABLE TO MODIFY THE PERCENTAGES.
BOOKING FORM:
9 | IN THE BOOKING FORM, KEEP A FACILITY TO SEARCH THE CUSTOMER BY EITHER SELECTING CUSTOMER NAME OR BY ENTERING MOBILE NO OR EMAIL ID. THE SYSTEM SHOULD DETECT DUPLICATION BY MATCHING NAME WITH MOBILE NO OR EMAIL ID.
10 | I SHOULD BE ABLE TO EDIT THE RATE EVEN AFTER I HAVE SAVED THE BOOKING.
11 | AT THE TIME OF BOOKING WHEN I CREATE A RECEIPT, THE NARRATION SHOULD BE TOWARDS INTEREST FREE DEPOSIT. ONCE THE FLAT IS REGISTERED THEN THE NARRATION OF THE INITIAL RECEIPT SHOULD AUTOMATICALLY BE UPDATED TO TOWARDS FLAT NO.
12 | IN THE BOOKING FORM THERE ARE 3 APPLICANTS
SO THERE SHOULD BE D.O.B. OF ALL 3 APPLICANTS AND PAN COPY OF ALL 3 APPLICANTS NO SPOUSE
13 | IN THE BOOKING FORM REMOVE TDS, REMOVE PARKING REQUIRED, NOT REQUIRED
14 | BROKERAGE PERCENTAGE 2% BY DEFAULT CACULATION TO BE ON AREA X RATE. IT SHOULD AUTO CALCULATE
15 | THERE SHOULD BE A FACILITY TO SELECT PAYMENT SCHEDULE FOR INDIVIDUAL CUSTOMER FROM THE TEMPLATE. IN ADDITION, I SHOULD BE ABLE TO MODIFY THE PERCENTAGES IF I WANT TO.
16 | ADD RTGS OPTION NEXT TO CASH/CHEQUE/DEMAND DRAFT
FOLLOW UP DETAILS:
17 | PUT A DATE RANGE INSTEAD OF AS ON DATE
ISSUE SUBJECT MASTER:
LOGIC:
18 | KARIA WANTS TO DEFINE AN ANSWER TO EVERY ISSUE. SO BELOW THE SUBJECT, ADD A TEXT BOX FOR THEM TO DEFINE THE ANSWER TO THAT QUESTION.
CUSTOMER GRIEVANCE:
19 | THE ORDER OF THE GRID TO BE CHANGED
PROJECT, CUSTOMER, FLAT NO……….RELATED TO, ISSUE
20 | WHEN I CLICK ON SAVE, THE SOFTWARE SHOULD AUTOMATICALLY SEND AN EMAIL AND SMS TO THE CUSTOMER
RECEIPT VOUCHER:
21 | IN THE RECEIPT VOUCHER THERE SHOULD BE A GRID
AMOUNT, TO BE ADJUSTED AGAINST.
PAYMENT FOLLOW UP:
22 | THE DATA OF ALL EMPLOYEES SHOULD BE VISIBLE TO ALL USERS.